## RVTM
Requirement Number | Requirement | Verification Method | Verification Level | Success Criteria | Verified By | Own Status | Status (rolled up)
1.2 | Ground Sample Distance | Test | System | MTF at Nyquist of at least 0.12 on the 4 m bar target. | TC-01 Ground Sample Distance Test (Passed) | Passed | Passed
1.3 | Swath Width | Test | Subsystem | Measured field of view of at least 2.52 degrees. | TC-02 Swath Width Measurement (Passed) | Passed | Passed
1.4 | Spectral Bands | Test | Subsystem | Four band edges inside 450–900 nm, each within 5 nm of design. | TC-03 Spectral Response Calibration (Passed) | Passed | Passed
1.5 | Daily Collection Volume | Analysis | System | Simulated daily volume of at least 3.2 GB over a 30-day plan. |  | Planned-only | Planned-only
1.6 | Revisit Time | Analysis | System | Coverage analysis shows a 72 h worst-case revisit. |  | Planned-only | Not Run
1.6.1 | Ground Track Repeat | Analysis | System | Orbit propagation shows a ground track repeat of 3 days ± 1 hour. | TC-13 Ground Track Repeat Analysis (Passed) | Passed | Passed
1.6.2 | Off-Nadir Imaging | Test | System | Targets at 25 degrees off nadir imaged with pointing error of at most 0.1 degrees. | TC-14 Off-Nadir Imaging Test (Not Run) | Not Run | Not Run
1.7 | Mission Lifetime | Analysis | System | Reliability and lifetime analysis shows at least 730 days at 0.8 probability. | TC-16 Lifetime Reliability Analysis (Passed) | Passed | Passed
2.1 | Pointing Accuracy | Test | Subsystem | Error of at most 0.1 degrees on each of 20 commanded targets. | TC-04 Pointing Accuracy Test (Failed) | Failed | Failed
2.2 | Pointing Stability | Test | Subsystem | Drift of at most 0.01 deg/s over each 40 s capture. | TC-04 Pointing Accuracy Test (Failed) | Failed | Failed
2.3 | Detumble | Test | Subsystem | Rates below 0.5 deg/s within 3 h from a 10 deg/s tip-off. | TC-05 Detumble Simulation (Passed) | Passed | Passed
2.4 | Target Slew | Analysis | Subsystem | Simulated 30 degree slew completes in 60 s or less. | TC-17 Slew Time Analysis (In Progress) | Not Run | Not Run
2.5 | Safe Mode Recovery |  |  |  |  | Unverified | Unverified
3.1 | Orbit Average Power | Test | Subsystem | End-of-life orbit-average power predicted from measured peak power. | TC-06 Solar Array Power Test (Passed) | Passed | Passed
3.2 | Battery Capacity | Test | Component | Measured capacity of at least 77 Wh at C/2 and 20 °C. | TC-07 Battery Capacity Test (Passed) | Passed | Passed
3.3 | Depth of Discharge | Test | Subsystem | Charge controller trips at 30% depth of discharge in each test orbit. | TC-07 Battery Capacity Test (Passed) | Passed | Passed
3.4 | Bus Regulation | Inspection | Component | Bus voltage stays within 11.76–12.24 V under all load steps. | TC-18 Bus Regulation Inspection (Passed) | Passed | Passed
3.5 | Battery Thermal Control |  |  |  |  | Unverified | Unverified
3.6 | Array Deployment | Test | Subsystem | Both panels latched within 45 min in the thermal vacuum deployment test. | TC-19 Array Deployment Test (Not Run) | Not Run | Not Run
4.1 | Onboard Storage | Test | Component | No bit errors over a 64 GB write and read-back. | TC-08 Onboard Storage Test (Passed) | Passed | Passed
4.2 | Command Execution | Test | Subsystem | All 500 time-tagged commands execute within 1 s of their tags. | TC-11 UHF Command Test (In Progress) | Not Run | Not Run
4.3 | Fault Detection | Test | Subsystem | Safe mode entered within 10 s in each undervoltage injection. | TC-09 Safe Mode Entry Test (Failed) | Failed | Failed
4.4 | Downlink Encryption | Inspection |  |  |  | Planned-only | Planned-only
5.1 | S-band Downlink Rate | Test | Subsystem | Frame error rate of at most 1e-6 at 10 Mbps through the RF suitcase. | TC-10 S-band Link Test (Not Run) | Not Run | Not Run
5.2 | UHF Command Uplink | Test | Subsystem | All 500 test commands received and decoded at 9.6 kbps. | TC-11 UHF Command Test (In Progress) | Not Run | Not Run
5.3 | Downlink Link Margin | Analysis | System | Link budget closes with at least 3 dB margin at 10 degrees elevation. | TC-10 S-band Link Test (Not Run) | Not Run | Not Run
5.4 | Daily Data Volume | Demonstration | System | Three consecutive days of at least 3 GB received in the end-to-end test. | TC-12 End-to-End Image Delivery (Not Run) | Not Run | Not Run
6.1 | Contact Scheduling | Demonstration | System | Contacts booked 48 h ahead for 14 consecutive days in rehearsal. | TC-20 Operations Rehearsal (Not Run) | Not Run | Not Run
6.2 | Image Delivery | Demonstration | System | Products on the portal within 6 h for 95% of passes in rehearsal. | TC-12 End-to-End Image Delivery (Not Run) | Not Run | Not Run
6.3 | Telemetry Archive | Inspection | System | Archive retention policy set to 730 days and checked by inspection. | TC-20 Operations Rehearsal (Not Run) | Not Run | Not Run
6.4 | Operator Interface |  |  |  |  | Unverified | Unverified
6.5 | Planning Cycle Time | Analysis | System | Monte Carlo simulation of the imaging pass meets 100 minutes with probability of at least 90%. |  | Planned-only | Planned-only